## 30 Mar
DATE: | 30.03.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, HARRISON, MAT, NICK
CHAIR: | ERIN
RECORDING: | https://web.microsoftstream.com/video/f0ca4da0-da26-429e-80f2-61502974de3c
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Establish meeting frequency/times |  | Tue 8:30pm, Thu 8:30pm | All | Tonight
Project goal consensus |  | Aiming for highest marks possible | All | Tonight
Team profile |  | Condense & paste own profile into GD | All | Thu 8:30pm
Github Repo created |  | Look into Git Kraken as alternative (https://www.gitkraken.com/) | Daniel
IT interview |  | Look at Canvas resource for questions | Harrison | Thu 8:30pm
Group website |  | Build group site | Erin & Nick
Question 1 |  | Vehicle automation | Daniel | Thu week 8:30pm
Question 2 |  | Cybersecurity | Nick | Thu week 8:30pm
Question 3 |  | Rasberry Pi | Matt | Thu week 8:30pm
Question 4 |  | Blockchain Edit: 03/04/2021 to Natural Language processing and chatterbots | Abby | Thu week 8:30pm
Project ideas |  | Everybody to review teammates project ideas & choose favourite: - Erin - Abby - Harrison - Nick - Matt - Dan | All | Thu 8:30pm
Team Profile Doc |  | Paste condensed personal info, ideal job etc here

## 1 Apr
DATE: | 01.04.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, HARRISON, MAT, NICK
CHAIR: | NICK
RECORDING: | https://web.microsoftstream.com/video/554c43c4-45ff-4be9-9b44-a3621522a506
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Progress update
IT Interview |  | Harrison to compile interviewee questions and transcribe once interview completed | Harrison | 6th of April
IT Interview |  | Organise the interviewee and conduct. | Abby | 13th of April
Team Profile |  | Team to finalise personal info and test results indvidually | All | 6th of April
Ideal Jobs |  | Team to indvidually summarise their ideal jobs and describe 4 or 5 skills needed for that job. Once done, a table will be created to contrast this. | All | 8th of April
IT Technologies |  | Abby, Daniel, Nick and Matt to have draft or final version of questions that have been assigned | Abby, Daniel, Nick and Matt | 8th of April
General Assignment |  | Decided to continue using Google Doc to write assignment, Nick will upload to GitHub every couple of days to historically track this. | Nick | N/A
Project Idea |  | Decided to move forward with Abby's project as the team project. | All (Abby leading) | N/A
General Assignment |  | Look into MS Teams or Trello to track when a componenet of the assignment is completed | Erin | 6th of April

## 6 Apr
DATE: | 06.04.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, HARRISON, MAT, NICK
CHAIR: | ABBY
RECORDING: | https://web.microsoftstream.com/video/b92cabfb-3721-4bb4-8145-86f8f5f0286b
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Quality Control |  | Once cards have been added into "Ready for Production" members are to add a QC checklist and tag Erin to conduct checks before uploading into the website. | Erin | n/a
Project Diagram |  | Project Idea Diagram - Artifact of the project's description | Daniel | 2021-04-13
Trello Board |  | Utilisation of Trello (Kanban) for project management. Includes: - Member and due date assignment; - QC Checklist; | team | n/a
Assigned Work Left To Do |  | Abby - Interview, Project Idea Daniel - Project Idea Erin - Website, QC, Project Idea Harrison - Interview, Project Idea Mathew - Industry Data, Ideal Jobs Nick - Industry Data, Ideal Jobs, Presentation, Website

## 12 Apr
DATE: | 08.04.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, HARRISON, MAT, NICK
CHAIR: | Mathew
RECORDING: | https://web.microsoftstream.com/video/9b354919-097c-4bc5-a48a-99356f5ad186
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
A2 extension request |  |  | Erin
Revisit project idea - Re-establish core functionality (infra>user or user>user communications?) - Is NFC tech necessary? QR/barcode possibly more realistic if infra>user model pursued
Consolidate A1 feedback into 1 doc, draw from this data moving forward
Additional artefacts - Project critical path (basic mindmap) - Competitor analysis (basic table) - Proof of concept (example of existing use case for our business model/concept)

## 14 Apr
DATE: | 14.04.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, NICK
CHAIR:
RECORDING: | https://web.microsoftstream.com/video/9b354919-097c-4bc5-a48a-99356f5ad186
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Meeting |  | Abby to meet with Thomas to discuss the project idea | Abby
Revisit project idea once more Have shifted the project idea focus to better prepare us for success in this and proceeding assignments. |  | Have decided to focus on NFC devices housed in restaurants Website for restaurants to upload their menu in native language App for customers to set their native language in-app, tap the NFC to access menu, order in own language. Possibly of building out the idea of restaurants using our software as a listing service (e.g like zomato, happy cow, etc). | Team

## 21 Apr
DATE: | 21.04.21
TIME: | 8:30PM AEST
PRESENT: | ABBY, DAN, ERIN, NICK, HARRISON, MAT
CHAIR: | Nick
RECORDING: | https://web.microsoftstream.com/video/138c9c82-762b-42bf-8749-7ff01f22eaf8
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Individual reflections |  | - Industry Data: This is at least half way done, just need to fill it out more.- Everyone needs to do 200 word group reflection and as a group, 400 words. - IT Work: Needs to be transcribed and questions answered. - IT Technologies: Abby and Mathew questions done and QC'd. - Project Idea: QC'd write up on the google doc ready to be put on website. | Team | Thu
Group reflection |  | Erin to draw commonalities from individuals & flesh out group reflection | Erin | Fri morn
Headshots |  | Team to submit for resizing | Erin | Thu
Logo |  | SVG animated file created & added to site | Erin | Fri morn
Slogan/Mission Statement |  | Spitball @ Friday meeting and add to site | Erin / Harrison | Friday

## 23 Apr
DATE: | 23.04.21
TIME: | 8:30PM AEST
PRESENT: | DAN, ERIN, NICK, HARRISON, MAT
CHAIR: | Nick
RECORDING: | https://web.microsoftstream.com/video/60044e87-1bd2-4129-bbaa-8c2850045b03
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Website copy |  | About us, Mission, Vision, Slogan | Erin | Friday 8pm
Group reflection |  | Remaining 2 reflections to be QC'd | Erin | Fri 8pm
Headshots |  | Tiles & titles created, added to website | Erin/Nick | Fri 8pm
Referenceing |  | AMA to Harvard | Harrison | Fri 8pm
Logo |  | Animated if poss | Erin | Fri 8pm
IT interview |  | Added to website | Nick | Fri 8pm
Github |  | Publish website | Nick | Fri 8pm
Skills |  | Section written | Dan | Fri 8pm
Motivation |  | Section written | Abby | Fri 8pm
Website |  | Final QC | Erin/Nick | Fri 10pm

## 29 Apr
DATE: | 29.04.21
TIME: | 8:30PM AEST
PRESENT: | DAN, ERIN, HARRISON, NICK
CHAIR: | ERIN
RECORDING: | https://web.microsoftstream.com/video/aa686ff3-7175-4c9e-aa9f-d6a19a2fdcf6
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Define project scope |  | Write Project Scope Statement | Team
TeamGantt |  | Send emails to Erin so she can invite to project (30-day free trial avail) | Team | Tomorrow
Artefacts |  | Discuss possible artefacts + software/systems needed to create them | Team
Sparkplus |  | Reminder submissions are due soon | Team | 2nd May
Scrum Methodology |  | -Self-organising, cross-functional team -Whole team makes decisions together, no leader -Project progresses by a series of time-constrained, pre-planned 'sprints' | Team
A2 Restrospective |  | -Run through QC submission requirements | Erin/team
Figma |  | Example prototype
A5 draft submission due |  | Storyboard: script, points we're planning to cover, essentially a mockup | Team
Work location |  | Google Doc: https://docs.google.com/document/d/1eZPpYAsVFKpaNNhVmOtQo1hn1YMHEqESihuJ7DMHEoY/edit# | Team
Infrastructure |  | Setup platforms
Team meetings |  | Confirmed new meeting time of Monday & Friday at 8PM to accomdate all team members | Team

## 3rd May
DATE: | 03.05.21
TIME: | 8:00PM AEST
PRESENT: | DAN, ERIN, NICK, HARRISON, MAT, ABBY
CHAIR: | NICK
RECORDING: | https://web.microsoftstream.com/video/f46e6b85-ccb5-496d-b964-90da15699f56
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
PM software |  | Switch from TeamGantt to Monday - Erin to invite team to join | Erin | 4th May 9am
App Map |  | Paper mockups + doc for page design & functionality | Erin & Nick
Scope Planning |  | Brainstorm and list all tasks & deliverables in the Project Scope Statement | Team
Video |  | Storyboard due end of this week, any takers on fleshing out script/talking points/paper mockups? | Mat
Division of Labour |  | Breakdown team into teams: - UI/UX Design: Erin & Nick - Research & Content writing team: Harrison, Dan & Abby - Production team: Mat - Project Management: Erin & Dan? | Team | Tonight

## 7th May
DATE: | 07.05.21
TIME: | 8:00PM AEST
PRESENT: | DAN, ERIN, NICK, HARRISON, MAT, ABBY
CHAIR: | Team
RECORDING: | https://web.microsoftstream.com/video/baa512d8-ca96-41b7-b3be-83674b398535
DESCRIPTION |  | OUTCOME | ASSIGNED TO | DEADLINE
Monday Update |  | Has anyone not joined the project? Erin to move tasks from SOW to Monday | Erin/team | Monday
A5 Storyboard |  | Script 3/4 complete, Mat to finish and produce storyboard this weekend | Mat | Sunday 5pm
Video |  | Mat to work exclusively on A5 moving forward to produce highest quality end result possible | Team | Saturday 8pm
Scope of Works doc |  | Almost complete, Erin to finish over the weekend | Erin | Monday meeting
Overview & Landscape section |  | Harrison working on Overview & researching landscape | Harrison | Friday meeting
Motivations |  | Global problems alleviated, mission statement | Abby
Gantt tute |  | Erin to post logins to TeamGantt to follow tutorials | Erin | Saturday morn
Plans & Progress |  | Almost completed | Dan
Aims |  | Dan to work on this over the weekend | Dan
Github |  | Fork A2 in Github, upload files to repo | Nick